## الملخص
DAM3-02-007 – مرفق ملاحظات التوريد على تحديث 06/10/2026
المصدر: تحديث P6 بتاريخ 06/10/2026 مقارنةً بالبرنامج المعتمد BL01-REV00
البند | القيمة | الشيت
عدد حالات تعارض أول توريد مع التوريد والفحص | 27 | 1 تعارض التوريد
عدد المواد التي بها هذا التعارض | 9 | 1 تعارض التوريد
عدد أعمال الموقع التي بدأت قبل التوريد | 28 | 2 أعمال قبل التوريد
عدد أنشطة التوريد المتأخرة عن الـ Baseline | 133 | 3 المواد المتأخرة في التوريد
متوسط أيام تأخير التوريد | 377.9474 | 3 المواد المتأخرة في التوريد
أقصى تأخير في التوريد (يوم) | 521 | 3 المواد المتأخرة في التوريد

## 1 تعارض التوريد
الملاحظة 1: نشاط «التوريد والفحص» بدأ أو اكتمل بينما نشاط «أول توريد» للمادة نفسها لم يبدأ
# | الشبكة | المادة (كما في الجدول) | كود نشاط أول توريد | اسم نشاط أول توريد (1ST Material Delivery) | حالته | كود نشاط التوريد والفحص | اسم نشاط التوريد والفحص (Material Delivery & Site Inspection) | حالته | نسبة الإنجاز
1 | شبكة الري | Valves – Irrigation Network | PRO-IR-1DL-110 | 1ST Material Delivery for Valves of Irrigation Network | لم يبدأ | PRO-R09-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | مكتمل | 100%
2 | شبكة الري | Valves – Irrigation Network | PRO-IR-1DL-110 | 1ST Material Delivery for Valves of Irrigation Network | لم يبدأ | PRO-R11-IR-DL-150 | Material Delivery & Site Inspection of Valves for Irrigation Network | مكتمل | 100%
3 | شبكة الري | Valves – Irrigation Network | PRO-IR-1DL-110 | 1ST Material Delivery for Valves of Irrigation Network | لم يبدأ | PRO-R14-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | مكتمل | 100%
4 | شبكة الري | Valves – Irrigation Network | PRO-IR-1DL-110 | 1ST Material Delivery for Valves of Irrigation Network | لم يبدأ | PRO-R19.2-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | مكتمل | 100%
5 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R09-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
6 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R10-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
7 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R11-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
8 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R14-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
9 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R15-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
10 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R16-RD-DL-130 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
11 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R17-RD-DL-110 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
12 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | PRO-R18-RD-DL-190 | Material Delivery & Site Inspection of Curbstones for Landscaping | مكتمل | 100%
13 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R09-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
14 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R10-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
15 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R11-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
16 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R14-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
17 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R15-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
18 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R16-RD-DL-120 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
19 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R17-RD-DL-100 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
20 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | PRO-R18-RD-DL-180 | Material Delivery & Site Inspection of Interlock Tiles for Landscaping | مكتمل | 100%
21 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-PW-1DL-130 | 1ST Material Delivery for Finishes of Potable Water Network | لم يبدأ | PRO-R14-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | مكتمل | 100%
22 | Sewage Pump Stations ( PS 06 ) | Civil Works – Sewage Pump Stations ( PS 06 ) | PRO-SPS-CV-1DL-10 | 1ST Material Delivery for Civil Works for Sewage Pump Stations ( PS 06 ) | لم يبدأ | PRO-SPS-CV-DL-10 | Material Delivery & Site Inspection for Civil Works for Sewage Pump Stations ( PS 06 ) | مكتمل | 100%
23 | Storm Drainage Ponds ( PO-J2 ) | Civil Works – Storm Drainage Ponds ( PO-J2 ) | PRO-DPO-CV-1DL-20 | 1ST Material Delivery for Civil Works for Storm Drainage Ponds ( PO-J2 ) | لم يبدأ | PRO-DPO-CV-DL-20 | Material Delivery & Site Inspection for Civil Works for Storm Drainage Ponds ( PO-J2 ) | جارٍ | 85%
24 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-SL-1DL-170 | 1ST Material Delivery for Cable Lugs of Street Lighting Network | لم يبدأ | PRO-R10-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | جارٍ | 80%
25 | شبكة إنارة الشوارع | Distrubution Panel Boards – Street Lighting Network | PRO-SL-1DL-160 | 1ST Material Delivery for Distrubution Panel Boards of Street Lighting Network | لم يبدأ | PRO-R09-SL-DL-160 | Material Delivery & Site Inspection of Distrubution Panel Boards for Street Lighting Network | مكتمل | 100%
26 | شبكة إنارة الشوارع | Distrubution Panel Boards – Street Lighting Network | PRO-SL-1DL-160 | 1ST Material Delivery for Distrubution Panel Boards of Street Lighting Network | لم يبدأ | PRO-R10-SL-DL-160 | Material Delivery & Site Inspection of Distrubution Panel Boards for Street Lighting Network | جارٍ | 80%
27 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-SL-1DL-130 | 1ST Material Delivery for Fuse Boxes of Street Lighting Network | لم يبدأ | PRO-R10-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | جارٍ | 80%

## 2 أعمال قبل التوريد
الملاحظة 2: أعمال موقع بدأت بينما نشاط توريد المادة المطلوبة لها لم يبدأ
# | الشبكة | كود نشاط التوريد | اسم نشاط التوريد | حالته | كود نشاط الموقع اللاحق | اسم نشاط الموقع | حالته | نسبة الإنجاز
1 | Sewage Pump Stations ( PS 06 ) | PRO-SPS-CV-1DL-10 | 1ST Material Delivery for Civil Works for Sewage Pump Stations ( PS 06 ) | لم يبدأ | CO-SW-PS7-MB-100 | Excavation Main Bulding | مكتمل | 100%
2 | اللاندسكيب | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | لم يبدأ | CO-R09.S01-RD-P-130 | Fixing of Interlock Tiles for Sidewalks Pavement-[Road 09] -[SW-1] | جارٍ | 50%
3 | اللاندسكيب | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | لم يبدأ | CO-R09.S01-RD-P-120 | Fixing of Curbstone for Sidewalks Pavement-[Road 09] -[SW-1] | مكتمل | 100%
4 | شبكة الجهد المتوسط | PRO-R10-MV-DL-120 | Material Delivery & Site Inspection of RMU Concrete Foundations for Medium Voltage Network | لم يبدأ | CO-R10.S03-ES-MV-150 | Installation Works for RMU Concrete Foundations of Medium Voltage Network-[Road 10]-[SW-3] | مكتمل | 100%
5 | شبكة الجهد المتوسط | PRO-R17-MV-DL-120 | Material Delivery & Site Inspection of RMU Concrete Foundations for Medium Voltage Network | لم يبدأ | CO-R17.S13-MV-150 | Installation Works for RMU Concrete Foundations of Medium Voltage Network-[Road 17]-[SW-13] | مكتمل | 100%
6 | شبكة الري | PRO-IR-1DL-110 | 1ST Material Delivery for Valves of Irrigation Network | لم يبدأ | CO-R09.S01-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 09] -[SW-1] | جارٍ | 20%
7 | شبكة الري | PRO-R15-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | لم يبدأ | CO-R15.S09-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 15]-[SW-9] | مكتمل | 100%
8 | شبكة الري | PRO-R16-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | لم يبدأ | CO-R16.S11-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 16]-[SW-11] | مكتمل | 100%
9 | شبكة الري | PRO-R17-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | لم يبدأ | CO-R17.S13-IR-120 | Installation Works for Main Line Valves of Irrigation Network-[Road 17]-[SW-13] | مكتمل | 100%
10 | شبكة الري | PRO-R18-IR-DL-130 | Material Delivery & Site Inspection of Valves for Irrigation Network | لم يبدأ | CO-R18.S15-IR-160 | Installation Works for Main Line Valves of Irrigation Network-[Road 18]-[SW-15] | مكتمل | 100%
11 | شبكة تصريف السيول | PRO-R09-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | لم يبدأ | CO-R09-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 09] | جارٍ | 75%
12 | شبكة تصريف السيول | PRO-R09-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | لم يبدأ | CO-R09-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 09] | جارٍ | 20%
13 | شبكة تصريف السيول | PRO-R09-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | لم يبدأ | CO-R09-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 09] | جارٍ | 85%
14 | شبكة تصريف السيول | PRO-R10-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | لم يبدأ | CO-R10-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 10] | مكتمل | 100%
15 | شبكة تصريف السيول | PRO-R10-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | لم يبدأ | CO-R10-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 10] | جارٍ | 20%
16 | شبكة تصريف السيول | PRO-R10-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | لم يبدأ | CO-R10-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 10] | جارٍ | 85%
17 | شبكة تصريف السيول | PRO-R11-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | لم يبدأ | CO-R11-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 11] | مكتمل | 100%
18 | شبكة تصريف السيول | PRO-R11-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | لم يبدأ | CO-R11-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 11] | جارٍ | 20%
19 | شبكة تصريف السيول | PRO-R11-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | لم يبدأ | CO-R11-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 11] | جارٍ | 85%
20 | شبكة تصريف السيول | PRO-R14-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | لم يبدأ | CO-R14-SD-TF-110 | Install Catch Basin Cover Works for External Finishes of Storm Drainage Network-[Road 14] | مكتمل | 100%
21 | شبكة تصريف السيول | PRO-R14-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | لم يبدأ | CO-R14-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 14] | مكتمل | 100%
22 | شبكة تصريف السيول | PRO-R15-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | لم يبدأ | CO-R15-SD-TF-100 | Testing Work for Pipes of Storm Drainage Network-[Road 15] | مكتمل | 100%
23 | شبكة تصريف السيول | PRO-R15-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | لم يبدأ | CO-R15-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 15] | مكتمل | 100%
24 | شبكة تصريف السيول | PRO-R16-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | لم يبدأ | CO-R16-SD-TF-120 | Main Manhole Internal Finishes (Benching + Insulation ) for Storm Drainage Network-[Road 16] | مكتمل | 100%
25 | شبكة مياه الشرب | PRO-R09-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | لم يبدأ | CO-R09.S02-PW-110 | Pipes Laying and accessories for Main Lines of Potable Water Network-[Road 09]-[SW-2] | جارٍ | 85%
26 | شبكة مياه الشرب | PRO-R14-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | لم يبدأ | CO-R14.S08-PW-210 | Insulation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 14]-[SW-8] | مكتمل | 100%
27 | شبكة مياه الشرب | PRO-R15-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | لم يبدأ | CO-R15.S10-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 15]-[SW-10] | مكتمل | 100%
28 | شبكة مياه الشرب | PRO-R16-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | لم يبدأ | CO-R16.S12-PW-210 | Installation Works for Main Line Valves and Valve Chambers of Potable Water Network-[Road 16]-[SW-12] | مكتمل | 100%

## 3 المواد المتأخرة في التوريد
أنشطة التوريد غير المكتملة والمتأخرة عن البرنامج المعتمد (أول توريد + التوريد والفحص)
# | الشبكة | المادة (كما في الجدول) | كود النشاط | اسم النشاط | نوع النشاط | الحالة | نسبة الإنجاز | الانتهاء في الـ Baseline | الانتهاء المتوقع | Total Float (يوم) | أيام التأخير
1 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-MV-1DL-120 | 1ST Material Delivery for Termination and Joints Kits of Medium Voltage Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-06-01 17:00 | 2026-11-04 17:00 | -295 | 521
2 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R09-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-19 17:00 | 2027-06-15 17:00 | -297 | 512
3 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R11-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-18 17:00 | 2027-07-15 17:00 | -297 | 512
4 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R10-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-19 17:00 | 2027-04-10 17:00 | -292 | 507
5 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R14-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-20 17:00 | 2027-05-10 17:00 | -292 | 506
6 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R16-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-18 17:00 | 2027-02-03 17:00 | -291 | 503
7 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R15-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-20 17:00 | 2027-03-07 17:00 | -293 | 503
8 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R17-MV-DL-110 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-08-19 17:00 | 2027-01-04 17:00 | -295 | 503
9 | شبكة الجهد المتوسط | Termination and Joints Kits – Medium Voltage Network | PRO-R18-MV-DL-130 | Material Delivery & Site Inspection of Termination and Joints Kits for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-07-20 17:00 | 2026-12-05 17:00 | -296 | 503
10 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-R10-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-10 17:00 | 2027-03-17 17:00 | -254 | 492
11 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-PW-1DL-130 | 1ST Material Delivery for Finishes of Potable Water Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-06-10 17:00 | 2026-10-12 17:00 | -258 | 489
12 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-R18-PW-DL-170 | Material Delivery & Site Inspection for Finishes of Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-07-10 17:00 | 2026-11-11 17:00 | -258 | 489
13 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-R16-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-09 17:00 | 2027-01-11 17:00 | -254 | 489
14 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-R17-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-08-10 17:00 | 2026-12-12 17:00 | -255 | 489
15 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-R15-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-11 17:00 | 2027-02-10 17:00 | -249 | 487
16 | شبكة مياه الشرب | Valves – Potable Water Network | PRO-R17-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-07-15 17:00 | 2026-11-04 17:00 | -291 | 477
17 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-R11-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-09 17:00 | 2027-05-23 17:00 | -260 | 468
18 | شبكة مياه الشرب | Finishes – Potable Water Network | PRO-R09-PW-DL-130 | Material Delivery & Site Inspection for Finishes of Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-10 17:00 | 2027-04-17 17:00 | -255 | 462
19 | شبكة مياه الشرب | Valves – Potable Water Network | PRO-R16-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-08-14 17:00 | 2026-11-04 17:00 | -291 | 447
20 | شبكة الري | Valves – Irrigation Network | PRO-IR-1DL-110 | 1ST Material Delivery for Valves of Irrigation Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-07-23 17:00 | 2026-10-12 17:00 | -265 | 446
21 | اللاندسكيب | Interlock Tiles – Landscaping | PRO-RD-1DL-140 | 1ST Material Delivery for Interlock Tiles of Landscaping | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-07-26 17:00 | 2026-10-12 17:00 | -256 | 443
22 | اللاندسكيب | Curbstones – Landscaping | PRO-RD-1DL-150 | 1ST Material Delivery for Curbstones of Landscaping | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-07-26 17:00 | 2026-10-12 17:00 | -256 | 443
23 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-SL-1DL-140 | 1ST Material Delivery for Lighting Fixtures of Street Lighting Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-07-31 17:00 | 2026-10-12 17:00 | -329 | 438
24 | شبكة إنارة الشوارع | Distrubution Panel Boards – Street Lighting Network | PRO-SL-1DL-160 | 1ST Material Delivery for Distrubution Panel Boards of Street Lighting Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-07-31 17:00 | 2026-10-12 17:00 | -127 | 438
25 | شبكة إنارة الشوارع | Lighting Earthing – Street Lighting Network | PRO-SL-1DL-150 | 1ST Material Delivery for Lighting Earthing of Street Lighting Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-07-31 17:00 | 2026-10-12 17:00 | -149 | 438
26 | Rising Main Network | Manholes Covers – Rising Main Network | PRO-R09-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Rising Main Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-07 17:00 | 2026-11-18 17:00 | -83 | 437
27 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-SL-1DL-170 | 1ST Material Delivery for Cable Lugs of Street Lighting Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-08-11 17:00 | 2026-10-22 17:00 | -323 | 437
28 | Rising Main Network | Membrane Insulation – Rising Main Network | PRO-R09-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Rising Main Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-07 17:00 | 2026-11-18 17:00 | -64 | 437
29 | شبكة إنارة الشوارع | Distrubution Panel Boards – Street Lighting Network | PRO-R10-SL-DL-160 | Material Delivery & Site Inspection of Distrubution Panel Boards for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 80% | 2025-08-31 17:00 | 2026-11-11 17:00 | -127 | 437
30 | شبكة إنارة الشوارع | Lighting Earthing – Street Lighting Network | PRO-R10-SL-DL-150 | Material Delivery & Site Inspection of Lighting Earthing for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-08-31 17:00 | 2026-11-11 17:00 | -144 | 437
31 | شبكة إنارة الشوارع | Lighting Earthing – Street Lighting Network | PRO-R09-SL-DL-150 | Material Delivery & Site Inspection of Lighting Earthing for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-08-31 17:00 | 2026-11-11 17:00 | -128 | 437
32 | شبكة الري | Valves – Irrigation Network | PRO-R18-IR-DL-130 | Material Delivery & Site Inspection of Valves for Irrigation Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-08-11 17:00 | 2026-10-13 17:00 | -265 | 428
33 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-SL-1DL-130 | 1ST Material Delivery for Fuse Boxes of Street Lighting Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-08-11 17:00 | 2026-10-12 17:00 | -322 | 427
34 | أعمال الطرق | Road Markings – Road Works | PRO-RD-1DL-170 | 1ST Material Delivery for Road Markings of Road Works | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-08-18 17:00 | 2026-10-12 17:00 | -225 | 420
35 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-RD-1DL-160 | 1ST Material Delivery for Traffic Signs Boards of Road Works | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-08-18 17:00 | 2026-10-12 17:00 | -256 | 420
36 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R18-SD-DL-190 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 0% | 2025-08-24 17:00 | 2026-10-17 17:00 | -146 | 419
37 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R18-SD-DL-230 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 0% | 2025-08-24 17:00 | 2026-10-17 17:00 | -111 | 419
38 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R18-SD-DL-210 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 0% | 2025-08-24 17:00 | 2026-10-17 17:00 | -125 | 419
39 | Sewage Pump Stations ( PS 06 ) | Civil Works – Sewage Pump Stations ( PS 06 ) | PRO-SPS-CV-1DL-10 | 1ST Material Delivery for Civil Works for Sewage Pump Stations ( PS 06 ) | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-09-29 17:00 | 2026-11-21 17:00 | -227 | 418
40 | شبكة الري | Valves – Irrigation Network | PRO-R17-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-08-30 17:00 | 2026-10-21 17:00 | -265 | 417
41 | شبكة مياه الشرب | Valves – Potable Water Network | PRO-R10-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 80% | 2025-10-15 17:00 | 2026-12-05 17:00 | -292 | 416
42 | شبكة مياه الشرب | Valves – Potable Water Network | PRO-R15-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-14 17:00 | 2026-11-04 17:00 | -291 | 416
43 | شبكة الصرف الصحي | Manholes Covers – Sewage Network | PRO-R11-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-23 17:00 | 2027-04-10 17:00 | -217 | 411
44 | شبكة الصرف الصحي | Manholes Covers – Sewage Network | PRO-R14-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-24 17:00 | 2027-03-07 17:00 | -214 | 407
45 | شبكة الصرف الصحي | Manholes Covers – Sewage Network | PRO-R10-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-24 17:00 | 2027-02-03 17:00 | -212 | 406
46 | شبكة الصرف الصحي | Manholes Covers – Sewage Network | PRO-R16-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-25 17:00 | 2026-12-05 17:00 | -217 | 406
47 | شبكة الصرف الصحي | Manholes Covers – Sewage Network | PRO-R17-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-24 17:00 | 2026-11-04 17:00 | -217 | 406
48 | شبكة الصرف الصحي | Manholes Covers – Sewage Network | PRO-R15-SW-DL-120 | Material Delivery & Site Inspection of Manholes Covers for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-24 17:00 | 2027-01-04 17:00 | -212 | 406
49 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R18-SL-DL-220 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-14 17:00 | 2026-10-24 17:00 | -329 | 405
50 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R17-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-15 17:00 | 2026-11-23 17:00 | -298 | 404
51 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R16-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-15 17:00 | 2026-12-23 17:00 | -297 | 403
52 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R17-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 0% | 2025-09-24 17:00 | 2026-10-28 17:00 | -125 | 399
53 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R17-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 0% | 2025-09-24 17:00 | 2026-10-28 17:00 | -141 | 399
54 | شبكة الري | Valves – Irrigation Network | PRO-R16-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-09-17 17:00 | 2026-10-21 17:00 | -265 | 399
55 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R17-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 0% | 2025-09-24 17:00 | 2026-10-28 17:00 | -111 | 399
56 | Storm Drainage Ponds ( PO-J2 ) | Civil Works – Storm Drainage Ponds ( PO-J2 ) | PRO-DPO-CV-DL-20 | Material Delivery & Site Inspection for Civil Works for Storm Drainage Ponds ( PO-J2 ) | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 85% | 2026-02-14 17:00 | 2027-03-17 17:00 | -289 | 396
57 | Storm Drainage Ponds ( PO-J2 ) | Civil Works – Storm Drainage Ponds ( PO-J2 ) | PRO-DPO-CV-1DL-20 | 1ST Material Delivery for Civil Works for Storm Drainage Ponds ( PO-J2 ) | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-11-24 17:00 | 2026-12-21 17:00 | -293 | 392
58 | شبكة الجهد المتوسط | RMU Concrete Foundations – Medium Voltage Network | PRO-MV-1DL-110 | 1ST Material Delivery for RMU Concrete Foundations of Medium Voltage Network | أول توريد (1ST Material Delivery) | لم يبدأ | 0% | 2025-11-10 17:00 | 2026-12-05 17:00 | -154 | 390
59 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R16-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-25 17:00 | 2026-11-16 17:00 | -111 | 387
60 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R16-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-25 17:00 | 2026-11-16 17:00 | -141 | 387
61 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R16-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-25 17:00 | 2026-11-16 17:00 | -125 | 387
62 | شبكة الري | Valves – Irrigation Network | PRO-R15-IR-DL-110 | Material Delivery & Site Inspection of Valves for Irrigation Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-07 17:00 | 2026-10-28 17:00 | -265 | 386
63 | شبكة مياه الشرب | Valves – Potable Water Network | PRO-R09-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-15 17:00 | 2027-01-04 17:00 | -292 | 385
64 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R09-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-05-19 17:00 | 2027-06-08 17:00 | -331 | 385
65 | شبكة مياه الشرب | Valves – Potable Water Network | PRO-R14-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-15 17:00 | 2026-12-05 17:00 | -292 | 385
66 | شبكة مياه الشرب | Valves – Potable Water Network | PRO-R11-PW-DL-110 | Material Delivery & Site Inspection of Valves for Potable Water Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-14 17:00 | 2027-02-03 17:00 | -169 | 385
67 | Storm Drainage Ponds ( PO-J1 ) | Civil Works – Storm Drainage Ponds ( PO-J1 ) | PRO-DPO-CV-DL-10 | Material Delivery & Site Inspection for Civil Works for Storm Drainage Ponds ( PO-J1 ) | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 97% | 2025-12-06 17:00 | 2026-12-26 17:00 | -91 | 385
68 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R10-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 80% | 2026-03-16 17:00 | 2027-04-03 17:00 | -331 | 383
69 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R11-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-06-23 17:00 | 2027-07-08 17:00 | -331 | 380
70 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R14-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-04-19 17:00 | 2027-05-03 17:00 | -326 | 379
71 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R15-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-14 17:00 | 2027-02-28 17:00 | -327 | 379
72 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R18-SL-DL-210 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-15 17:00 | 2026-10-28 17:00 | -329 | 378
73 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R17-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-15 17:00 | 2026-12-28 17:00 | -329 | 378
74 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R09-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-16 17:00 | 2027-03-29 17:00 | -294 | 378
75 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R16-SL-DL-170 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-14 17:00 | 2027-01-27 17:00 | -329 | 378
76 | شبكة إنارة الشوارع | Cable Lugs – Street Lighting Network | PRO-R18-SL-DL-250 | Material Delivery & Site Inspection of Cable Lugs for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-15 17:00 | 2026-11-28 17:00 | -329 | 378
77 | شبكة الصرف الصحي | Membrane Insulation – Sewage Network | PRO-R11-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-29 17:00 | 2027-04-10 17:00 | -214 | 377
78 | شبكة الصرف الصحي | Membrane Insulation – Sewage Network | PRO-R14-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-23 17:00 | 2027-03-07 17:00 | -210 | 377
79 | شبكة الصرف الصحي | Membrane Insulation – Sewage Network | PRO-R16-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-24 17:00 | 2026-12-05 17:00 | -214 | 376
80 | شبكة الصرف الصحي | Membrane Insulation – Sewage Network | PRO-R15-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-24 17:00 | 2027-01-04 17:00 | -209 | 376
81 | شبكة الصرف الصحي | Membrane Insulation – Sewage Network | PRO-R17-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-10-25 17:00 | 2026-11-04 17:00 | -213 | 375
82 | شبكة الصرف الصحي | Membrane Insulation – Sewage Network | PRO-R10-SW-DL-130 | Material Delivery & Site Inspection of Membrane Insulation for Sewage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-24 17:00 | 2027-02-03 17:00 | -209 | 375
83 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R10-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-14 17:00 | 2027-01-23 17:00 | -294 | 374
84 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R11-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-04-19 17:00 | 2027-04-28 17:00 | -219 | 374
85 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R14-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-14 17:00 | 2027-02-23 17:00 | -295 | 374
86 | شبكة إنارة الشوارع | Lighting Fixtures – Street Lighting Network | PRO-R15-SL-DL-140 | Material Delivery & Site Inspection of Lighting Fixtures for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-15 17:00 | 2026-12-23 17:00 | -297 | 373
87 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R17-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-15 17:00 | 2026-11-11 17:00 | -272 | 361
88 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R15-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-24 17:00 | 2026-11-16 17:00 | -141 | 357
89 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R15-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-24 17:00 | 2026-11-16 17:00 | -111 | 357
90 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R15-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-11-24 17:00 | 2026-11-16 17:00 | -125 | 357
91 | شبكة الجهد المتوسط | RMU Concrete Foundations – Medium Voltage Network | PRO-R10-MV-DL-120 | Material Delivery & Site Inspection of RMU Concrete Foundations for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-19 17:00 | 2027-01-04 17:00 | -154 | 350
92 | شبكة الجهد المتوسط | RMU Concrete Foundations – Medium Voltage Network | PRO-R17-MV-DL-120 | Material Delivery & Site Inspection of RMU Concrete Foundations for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-04 17:00 | 2027-02-17 17:00 | -154 | 350
93 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R11-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-05-19 17:00 | 2027-04-17 17:00 | -244 | 333
94 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R09-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-04-19 17:00 | 2027-03-17 17:00 | -268 | 332
95 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R15-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-14 17:00 | 2026-12-12 17:00 | -272 | 332
96 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R14-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-16 17:00 | 2027-02-10 17:00 | -268 | 331
97 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R16-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-15 17:00 | 2026-11-11 17:00 | -272 | 331
98 | شبكة إنارة الشوارع | Fuse Boxes – Street Lighting Network | PRO-R10-SL-DL-130 | Material Delivery & Site Inspection of Fuse Boxes for Street Lighting Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 80% | 2026-02-14 17:00 | 2027-01-11 17:00 | -268 | 331
99 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R10-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-24 17:00 | 2026-11-16 17:00 | -111 | 327
100 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R10-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-24 17:00 | 2026-11-16 17:00 | -125 | 327
101 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R10-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2025-12-24 17:00 | 2026-11-16 17:00 | -141 | 327
102 | شبكة الجهد المتوسط | Medium Voltage Cables – Medium Voltage Network | PRO-R09-MV-DL-100 | Material Delivery & Site Inspection of Medium Voltage Cables for Medium Voltage Network | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 90% | 2025-12-20 17:00 | 2026-11-04 17:00 | -198 | 319
103 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R14-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-24 17:00 | 2026-11-16 17:00 | -111 | 296
104 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R09-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-23 17:00 | 2026-12-16 17:00 | -141 | 296
105 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R14-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-24 17:00 | 2026-11-16 17:00 | -125 | 296
106 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R09-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-23 17:00 | 2026-12-16 17:00 | -125 | 296
107 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R09-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-23 17:00 | 2026-12-16 17:00 | -111 | 296
108 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R14-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-24 17:00 | 2026-11-16 17:00 | -141 | 296
109 | شبكة تصريف السيول | Epoxy Insulation – Storm Drainage Network | PRO-R11-SD-DL-160 | Material Delivery & Site Inspection of Epoxy Insulation for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-29 17:00 | 2027-01-16 17:00 | -110 | 293
110 | شبكة تصريف السيول | Manholes Covers – Storm Drainage Network | PRO-R11-SD-DL-140 | Material Delivery & Site Inspection of Manholes Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-29 17:00 | 2027-01-16 17:00 | -125 | 293
111 | شبكة تصريف السيول | Catch Basin Covers – Storm Drainage Network | PRO-R11-SD-DL-150 | Material Delivery & Site Inspection of Catch Basin Covers for Storm Drainage Network | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-29 17:00 | 2027-01-16 17:00 | -125 | 293
112 | أعمال الطرق | Road Markings – Road Works | PRO-R14-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-08-04 17:00 | 2027-05-23 17:00 | -258 | 292
113 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R11-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-09-03 17:00 | 2027-06-22 17:00 | -226 | 292
114 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R09-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-08-04 17:00 | 2027-05-23 17:00 | -227 | 292
115 | أعمال الطرق | Road Markings – Road Works | PRO-R09-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-09-03 17:00 | 2027-06-22 17:00 | -257 | 292
116 | أعمال الطرق | Road Markings – Road Works | PRO-R11-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-10-05 17:00 | 2027-07-22 17:00 | -256 | 290
117 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R17-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-25 17:00 | 2026-12-12 17:00 | -252 | 290
118 | أعمال الطرق | Road Markings – Road Works | PRO-R18-RD-DL-210 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-02-25 17:00 | 2026-12-12 17:00 | -252 | 290
119 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R18-RD-DL-200 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-01-26 17:00 | 2026-11-11 17:00 | -255 | 289
120 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R15-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-04-30 17:00 | 2027-02-10 17:00 | -217 | 286
121 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R14-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-07-05 17:00 | 2027-04-17 17:00 | -222 | 286
122 | أعمال الطرق | Road Markings – Road Works | PRO-R15-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-06-04 17:00 | 2027-03-17 17:00 | -252 | 286
123 | أعمال الطرق | Road Markings – Road Works | PRO-R17-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-31 17:00 | 2027-01-11 17:00 | -252 | 286
124 | أعمال الطرق | Road Markings – Road Works | PRO-R16-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-04-30 17:00 | 2027-02-10 17:00 | -247 | 286
125 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R16-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-31 17:00 | 2027-01-11 17:00 | -217 | 286
126 | أعمال الطرق | Road Markings – Road Works | PRO-R10-RD-DL-150 | Material Delivery & Site Inspection of Road Markings For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-07-05 17:00 | 2027-04-17 17:00 | -252 | 286
127 | أعمال الطرق | Traffic Signs Boards – Road Works | PRO-R10-RD-DL-140 | Material Delivery & Site Inspection of Traffic Signs Boards For Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-06-04 17:00 | 2027-03-17 17:00 | -221 | 286
128 | Sewage Pump Stations ( PS06 ) | Electromechanical Works – Sewage Pump Stations ( PS06 ) | PRO-SPS7-LL-MSI-10 | Material Site Inspection for Electromechanical Works for Sewage Pump Stations ( PS06 ) | التوريد والفحص (Material Delivery & Site Inspection) | جارٍ | 30% | 2026-08-31 17:00 | 2027-05-08 17:00 | -206 | 250
129 | Sewage Pump Stations ( PS 06 ) | Electromechanical Works – Sewage Pump Stations ( PS 06 ) | PRO-SPS7-LL-SH/DL-10 | Material Delivery for Electromechanical Works for Sewage Pump Stations ( PS 06 ) | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-07-04 17:00 | 2027-03-07 17:00 | -203 | 246
130 | أعمال الطرق | Prime Coat – Road Works | PRO-R10-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-03-31 17:00 | 2026-11-11 17:00 | -57 | 225
131 | أعمال الطرق | Bituminous Base & Wearing Courses – Road Works | PRO-R10-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-04-30 17:00 | 2026-11-11 17:00 | -95 | 195
132 | أعمال الطرق | Prime Coat – Road Works | PRO-R09-RD-DL-160 | Material Delivery & Site Inspection for Prime Coat of Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-06-04 17:00 | 2026-12-12 17:00 | -56 | 191
133 | أعمال الطرق | Bituminous Base & Wearing Courses – Road Works | PRO-R09-RD-DL-170 | Material Delivery & Site Inspection for Bituminous Base & Wearing Courses of Road Works | التوريد والفحص (Material Delivery & Site Inspection) | لم يبدأ | 0% | 2026-07-05 17:00 | 2026-12-12 17:00 | -96 | 160